Questions for Assessing Trial Feasibility

Questions to Ask Yourself or Your Team

Participant Population and Recruitment

- Do we have access to the participant population described in the trial eligibility criteria?

- How would we identify and recruit eligible participants?

- Approximately how many eligible participants do we have access to?

- How often do we see this patient population?

- What proportion of eligible participants are likely to enrol in the trial?

Study Design and Procedures

- Are the study procedures part of routine clinical care?

- Which study procedures are additional to routine clinical care?

- Will the additional procedures provide valuable information to support the trial objectives?

Investigational Product/Intervention

- What information has been provided about the investigational product, device or intervention?

- Do we have enough information to understand the investigational product, device or intervention?

- Does the investigational product, device or intervention address an unmet clinical need?

Evidence and Safety

- What previous clinical studies have been conducted for this product, device or intervention?

- What is known about its safety profile and how it is metabolised?

- Are there any safety concerns that could affect trial delivery or participant wellbeing?

Questions to Ask the CRO

Local Presence and Experience

- Does the CRO have staff based in Australia?

- What roles do the Australian based staff perform?

- Has the CRO supported clinical trials in Australia previously?

- Does the CRO have experience in this therapeutic area?

- Does the CRO have experience managing first in human or early phase studies?

Study Team and Support

- Does the CRO have sufficient staff to support the study?

- Who will manage the project on a day-to-day basis?

- Who is the primarily contact for operational issues?

- Who is the escalation contact if issues cannot be resolved?

- Has the CRO assembled an appropriately qualified project team for the study?

Sponsor Relationship

- Has the CRO worked with this sponsor before?

- What has been the CRO’s experience working with the sponsor?

Financial and Operational Management

- What are the CRO’s payment terms with research sites?

- Are site payments dependent on the CRO receiving payment for the sponsor?

- Does the CRO have adequate systems and financial capacity to support timely payments?

- What information is the CRO seeking through the request for proposal (RFP) costs?

- Does the CRO have realistic expectations about trial costs?

Governance

- Who is responsible for maintaining the study timeline?

- Who makes key decisions when issues arise during the study?

- What is the process for escalating operational issues?

Questions to Ask the Sponsor

Organisation and Funding

- Does the sponsor have an Australian legal entity?

- What is the sponsor’s current funding status?

- Who are the sponsor’s major investors or funding partners?

- Is the study fully funded through to completion?

- Is continuation of the study dependent on future financing?

Capability

- Has the sponsor conducted previous clinical trials?

- Does the sponsor have experience in developing this type of product or therapy?

- How will the investigational product be manufactured?

- Has the sponsor completed the necessary pre-clinical studies?

- Has the sponsor identified any outstanding pre-clinical evidence requirements?

Study Support and Delivery

- Does the sponsor have dedicated staff to support the trial?

- Has the sponsor appointed a CRO for the study?

- If a CRO has not been appointed, when will one be engaged?

Trial Planning

- What information is the sponsor seeking through the RFP process?

- Does the sponsor have realistic expectations about trial costs?

Reputation and Reliability

- Is information about the sponsor publicly available and up to date?

- Can the sponsor demonstrate a history of delivering clinical research projects?

- Have other research sites reported positive experiences working with the sponsor?

- Does the sponsor have a reliable history of making payments on time?

- Will the contracting entity be the same organisation presenting the opportunity?